## Sheet1
Task # | Sprint 1 Backlog Tasks | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
| Guideline | 29 | 25 | 20 | 15 | 10 | 5 | 0
| Remaining Values | 29 | 23 | 15 | 13 | 10 | 7 | 0
1 | Research (Image Processing Techniques) in Iris Analysing field | 6 | 0 | 0 | 0 | 0 | 0 | 0
2 | Complete literature review for supervisor | 3 | 3 | 0 | 0 | 0 | 0 | 0
3 | Research (Deep Learning Basics) in Iris Analysing field | 7 | 7 | 2 | 0 | 0 | 0 | 0
|  | 3 | 3 | 3 | 3 | 0 | 0 | 0
|  | 10 | 10 | 10 | 10 | 10 | 7 | 0
| Sprint 2 Backlog Tasks | Week 1: Week 8; Week 2: Week 9; Week 3: Week 10; Week 4: Week 11
| Guideline | Week 1: 46; Week 2: 30; Week 3: 15; Week 4: 0
| Remaining Values | Week 1: 46; Week 2: 32; Week 3: 15; Week 4: 7
|  | 5 | 0 | 0 | 0
|  | 4 | 0 | 0 | 0
|  | 5 | 0 | 0 | 0
|  | 12 | 12 | 0 | 0
|  | 10 | 10 | 10 | 7
|  | 10 | 10 | 5 | 0